## Table Of Contents
Table Of Contents
Table Of Contents
Dashboard
RAG Status
Project Manager Status
Task Counts
Tables
Schedule
Raw Schedule
File Info

## Dashboard
Last Update 10-08-2021 |  | Return to the table of contents
Total Status Light--> | 30.59% | Key Status Light Value--> | 29.31% | Critical Path Status Light--> | 66.67% | Set Value Ranges
[6 empty] | Min | Max
red | #N/A | red | #N/A | red | 1 | 41% | 100%
orange | 1 | orange | #N/A | orange | #N/A | 30% | 40%
green | #N/A | green | 1 | green | #N/A | 0% | 30%
| Status | Percentage
Red | 26 | 30.5882
Amber | 20 | 23.5294
Green | 39 | 45.8824

## RAG Status
Last Update 10-08-2021 | Return to the table of contents
|  | Total Status Light--> | 30.59% | Key Status Light Value--> | 29.31% | Critical Path Status Light--> | 66.67% | Set Value Ranges
[8 empty] | Min | Max
|  |  | #N/A | red | #N/A |  | 1 | 41% | 100%
|  |  | 1 | orange | #N/A |  | #N/A | 30% | 40%
|  |  | #N/A | green | 1 |  | #N/A | 0% | 30%

## Project Manager Status
Last Update 10-08-2021 | Return to the table of contents

## Task Counts
Last Update 10-08-2021 | Return to the table of contents

## Tables
Last Update 10-08-2021 |  | Return to the table of contents
Hub by Status |  |  |  |  | Key Milestone Count |  |  | Key Milestone by PM |  |  |  |  | Row Labels | Count of Hub +
Quanty |  |  |  |  | Key | Quantity |  | Key Deliverable + | (All) |  |  |  | Go Live | 19
Hub | Red | Amber | Green | Total | Yes | 58 | [6 empty] | Implementation | 30
Go Live | 2 | 3 | 10 | 15 | No | 27 |  | Quantity | Column Labels |  |  |  | Planning | 63
Implementation | 9 | 3 | 15 | 27 | Total | 85 |  | PM | Carolyn | Jeff | Kathy | Total | Grand Total | 112
Planning | 15 | 14 | 14 | 43 |  |  |  | Red | 6 | 2 | 18 | 26
Total | 26 | 20 | 39 | 85 | Key Deliverable + | Yes |  | Amber | 3 | 3 | 14 | 20 | Row Labels | Count of Work Stream +
[8 empty] | Green | 7 | 10 | 22 | 39 | Band | 16
[5 empty] | Status | Quantity | Percentage | Total | 16 | 15 | 54 | 85 | Creative | 3
Work Stream by Status |  |  |  |  | Red | 17 | 29.31% | [5 empty] | Finance and Accounting | 12
Quantity |  |  |  |  | Amber | 13 | 22.41% | Key Deliverable + | Yes |  |  |  | Human Resources | 6
Work Stream | Red | Amber | Green | Total | Green | 28 | 48.28% | [5 empty] | Logistics | 9
Band | 3 | 3 | 10 | 16 | Total | 58 | 100% | Count of RAG Staus |  |  |  |  | Manager | 18
Creative | 1 | 1 | 1 | 3 |  |  |  | PM | Red | Amber | Green | Total | PR | 9
Finance and Accounting | 4 |  | 8 | 12 | Key Deliverable + | No |  | Carolyn | 4 | 1 | 5 | 10 | PR/Band | 3
Human Resources | 2 | 2 | 2 | 6 |  |  |  | Jeff | 2 | 3 | 10 | 15 | Travel | 6
Logistics | 3 | 3 | 3 | 9 | Status | Quantity | Percentage | Kathy | 11 | 9 | 13 | 33 | Vendor | 3
Manager | 6 | 5 | 7 | 18 | Red | 9 | 33.33% | Total | 17 | 13 | 28 | 58 | Grand Total | 85
PR | 3 | 3 | 3 | 9 | Amber | 7 | 25.93%
PR/Band | 1 |  | 2 | 3 | Green | 11 | 40.74% | Key Deliverable + | No
Travel | 2 | 2 | 2 | 6 | Total | 27 | 100%
Vendor | 1 | 1 | 1 | 3 |  |  |  | Count of RAG Staus
Total | 26 | 20 | 39 | 85 | Key Deliverable + | (All) |  | PM | Red | Amber | Green | Total
[8 empty] | Carolyn | 2 | 2 | 2 | 6
Critical Path | Yes |  |  |  | Status | Quantity | Percentage | Kathy | 7 | 5 | 9 | 21
[5 empty] | Red | 26 | 30.59% | Total | 9 | 7 | 11 | 27
Row Labels | Count of Critical | Percentage |  |  | Amber | 20 | 23.53%
Red | 2 | 66.67% |  |  | Green | 39 | 45.88%
Green | 1 | 33.33% |  |  | Total | 85 | 100%
Grand Total | 3 | 100%

## Schedule
Last Update 10-08-2021 |  | Return to the table of contents
Critical | Summary | Unique ID | % Complete | Days Until Start + | Days Until Finish + | Days Since Completed + | Hub + | Work Stream + | PM + | Task Name | Start | Finish | Actual Start + | Actual Finish + | Duration | Key Deliverable + | Predecessors | Active | RAG + | RAG Staus
No | No | 32 | 1 | -127 | -97 | 97 | Planning | Travel | Kathy | Hotels | 2021-02-10 | 2021-03-23 | 2021-02-10 | 2021-03-23 | 30 | Yes | 37FS-120 days | Yes | -127 | Red
No | No | 31 | 1 | -127 | -97 | 97 | Planning | Travel | Kathy | Transportation | 2021-02-10 | 2021-03-23 | 2021-02-10 | 2021-03-23 | 30 | Yes | 37FS-120 days | Yes | -127 | Red
No | No | 36 | 1 | -129 | -39 | 39 | Planning | Manager | Kathy | Contracts | 2021-02-08 | 2021-06-10 | 2021-02-08 | 2021-06-10 | 90 | Yes | 37FS-120 days | Yes | -129 | Red
No | No | 37 | 1 | -129 | -39 | 39 | Planning | Manager | Kathy | Ryders | 2021-02-08 | 2021-06-10 | 2021-02-08 | 2021-06-10 | 90 | Yes | 37FS-120 days | Yes | -129 | Red
No | No | 33 | 1 | -96 | -36 | 36 | Planning | Manager | Kathy | Vehice Leasing | 2021-03-25 | 2021-06-15 | 2021-03-25 | 2021-06-15 | 60 | No | 37FS-120 edays | Yes | -96 | Red
No | No | 35 | 1 | -96 | -66 | 66 | Planning | Manager | Kathy | Licensing and Insurance | 2021-03-25 | 2021-05-04 | 2021-03-25 | 2021-05-04 | 30 | No | 37FS-120 edays | Yes | -96 | Red
No | No | 39 | 1 | -129 | -99 | 99 | Planning | Human Resources | Kathy | Hiring | 2021-02-08 | 2021-03-19 | 2021-02-08 | 2021-03-19 | 30 | Yes | 37FS-120 days | Yes | -129 | Red
No | No | 38 | 1 | -129 | -99 | 99 | Planning | Human Resources | Kathy | Training | 2021-02-08 | 2021-03-19 | 2021-02-08 | 2021-03-19 | 30 | No | 37FS-120 days | Yes | -129 | Red
No | No | 41 | 1 | -129 | -39 | 39 | Planning | Logistics | Kathy | Rentals | 2021-02-08 | 2021-06-10 | 2021-02-08 | 2021-06-10 | 90 | Yes | 37FS-120 days | Yes | -129 | Red
No | No | 42 | 1 | -129 | -39 | 39 | Planning | Logistics | Kathy | Purchasing | 2021-02-08 | 2021-06-10 | 2021-02-08 | 2021-06-10 | 90 | Yes | 37FS-120 days | Yes | -129 | Red
No | No | 40 | 1 | -129 | -99 | 99 | Planning | Logistics | Kathy | Shipping - Venue to Venue | 2021-02-08 | 2021-03-19 | 2021-02-08 | 2021-03-19 | 30 | Yes | 37FS-120 days | Yes | -129 | Red
No | No | 9 | 1 | -129 | -28 | 28 | Planning | Creative | Kathy | Promotional Artwork | 2021-02-08 | 2021-06-25 | 2021-02-08 | 2021-06-25 | 101 | No | 37FS-120 days | Yes | -129 | Red
No | No | 43 | 1 | -129 | -74 | 74 | Planning | Vendor | Kathy | Proof Design | 2021-02-08 | 2021-04-23 | 2021-02-08 | 2021-04-23 | 55 | No | 37FS-120 days | Yes | -129 | Red
No | No | 44 | 1 | -74 | -48 | 48 | Planning | Manager | Kathy | Design Approvals | 2021-04-26 | 2021-05-28 | 2021-04-26 | 2021-05-28 | 26 | Yes | 22 | Yes | -74 | Red
No | No | 46 | 0 | -178 | 107 |  | Implementation | Finance and Accounting | Kathy | Payroll | 2020-12-01 | 2021-12-31 | 2020-12-01 |  | 285 | Yes |  | Yes | -178 | Red
No | No | 45 | 0 | -178 | 107 |  | Implementation | Finance and Accounting | Kathy | Taxes | 2020-12-01 | 2021-12-31 | 2020-12-01 |  | 285 | Yes |  | Yes | -178 | Red
No | No | 48 | 0 | -178 | 107 |  | Implementation | Finance and Accounting | Kathy | Accounts recivable | 2020-12-01 | 2021-12-31 | 2020-12-01 |  | 285 | No |  | Yes | -178 | Red
No | No | 47 | 0 | -178 | 107 |  | Implementation | Finance and Accounting | Kathy | Accounts Payable | 2020-12-01 | 2021-12-31 | 2020-12-01 |  | 285 | No |  | Yes | -178 | Red
Yes | No | 49 | 0 | -150 | 4 |  | Planning | Band | Carolyn | Rehearsals | 2021-01-08 | 2021-08-10 | 2021-01-08 |  | 154 | Yes | 37FS-240 days | Yes | -150 | Red
No | No | 50 | 0 | -69 | 81 |  | Implementation | Manager | Carolyn | Ticket Sales | 2021-05-01 | 2021-11-25 | 2021-05-01 |  | 150 | Yes |  | Yes | -69 | Red
No | No | 51 | 0 | -178 | -24 |  | Implementation | PR | Carolyn | Promotional events | 2020-12-01 | 2021-07-01 | 2020-12-01 |  | 154 | Yes |  | Yes | -178 | Red
No | No | 56 | 0 | -155 | 81 |  | Implementation | PR | Carolyn | Radio advertising buys | 2021-01-01 | 2021-11-25 | 2021-01-01 |  | 236 | No |  | Yes | -155 | Red
No | No | 55 | 0 | -155 | 81 |  | Implementation | PR | Carolyn | TV advertising buys | 2021-01-01 | 2021-11-25 | 2021-01-01 |  | 236 | No |  | Yes | -155 | Red
No | No | 54 | 0 | -178 | 81 |  | Implementation | PR/Band | Carolyn | Promotional Interviews | 2020-12-01 | 2021-11-25 | 2020-12-01 |  | 259 | Yes |  | Yes | -178 | Red
Yes | No | 20 | 0 | -24 | -9 |  | Go Live | Band | Jeff | New York, NY | 2021-07-02 | 2021-07-22 | 2021-07-02 |  | 15 | Yes |  | Yes | -24 | Red
No | No | 19 | 0 | -7 | 13 |  | Go Live | Band | Jeff | Philadelphia, PA | 2021-07-27 | 2021-08-23 | 2021-07-27 |  | 20 | Yes | 37FS+2 days | Yes | -7 | Red
No | No | 18 | 0 | 15 | 39 |  | Go Live | Band | Jeff | Washington, DC | 2021-08-26 | 2021-09-28 |  |  | 24 | Yes | 38FS+2 days | Yes | 15 | Amber
No | No | 17 | 0 | 41 | 51 |  | Go Live | Band | Jeff | New Orleans, LA | 2021-10-01 | 2021-10-14 |  |  | 10 | Yes | 39FS+2 days | Yes | 41 | Amber
No | No | 22 | 0 | 56 | 66 |  | Go Live | Band | Jeff | Austin, TX | 2021-10-22 | 2021-11-04 |  |  | 10 | Yes | 40FS+5 days | Yes | 56 | Amber
No | No | 21 | 0 | 71 | 81 |  | Go Live | Band | Jeff | Los Angeles, CA | 2021-11-12 | 2021-11-25 |  |  | 10 | Yes | 41FS+5 days | Yes | 71 | Green
No | No | 92 | 0 | 40 | 70 |  | Planning | Travel | Kathy | Hotels | 2021-09-30 | 2021-11-10 |  |  | 30 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 93 | 0 | 40 | 70 |  | Planning | Travel | Kathy | Transportation | 2021-09-30 | 2021-11-10 |  |  | 30 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 95 | 0 | 40 | 130 |  | Planning | Manager | Kathy | Contracts | 2021-09-30 | 2022-02-02 |  |  | 90 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 96 | 0 | 40 | 130 |  | Planning | Manager | Kathy | Ryders | 2021-09-30 | 2022-02-02 |  |  | 90 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 98 | 0 | 40 | 100 |  | Planning | Manager | Kathy | Vehice Leasing | 2021-09-30 | 2021-12-22 |  |  | 60 | No | 78FS-120 edays | Yes | 40 | Amber
No | No | 99 | 0 | 40 | 70 |  | Planning | Manager | Kathy | Licensing and Insurance | 2021-09-30 | 2021-11-10 |  |  | 30 | No | 78FS-120 edays | Yes | 40 | Amber
No | No | 101 | 0 | 40 | 70 |  | Planning | Human Resources | Kathy | Hiring | 2021-09-30 | 2021-11-10 |  |  | 30 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 102 | 0 | 40 | 70 |  | Planning | Human Resources | Kathy | Training | 2021-09-30 | 2021-11-10 |  |  | 30 | No | 78FS-120 edays | Yes | 40 | Amber
No | No | 104 | 0 | 40 | 130 |  | Planning | Logistics | Kathy | Rentals | 2021-09-30 | 2022-02-02 |  |  | 90 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 105 | 0 | 40 | 130 |  | Planning | Logistics | Kathy | Purchasing | 2021-09-30 | 2022-02-02 |  |  | 90 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 106 | 0 | 40 | 70 |  | Planning | Logistics | Kathy | Shipping - Venue to Venue | 2021-09-30 | 2021-11-10 |  |  | 30 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 108 | 0 | 40 | 130 |  | Planning | Creative | Kathy | Promotional Artwork | 2021-09-30 | 2022-02-02 |  |  | 90 | No | 78FS-120 edays | Yes | 40 | Amber
No | No | 109 | 0 | 40 | 70 |  | Planning | Vendor | Kathy | Proof Design | 2021-09-30 | 2021-11-10 |  |  | 30 | No | 78FS-120 edays | Yes | 40 | Amber
No | No | 110 | 0 | 40 | 54 |  | Planning | Manager | Kathy | Design Approvals | 2021-09-30 | 2021-10-19 |  |  | 14 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 112 | 0 | 84 | 367 |  | Implementation | Finance and Accounting | Kathy | Payroll | 2021-12-01 | 2022-12-31 |  |  | 283 | Yes |  | Yes | 84 | Green
No | No | 113 | 0 | 84 | 367 |  | Implementation | Finance and Accounting | Kathy | Taxes | 2021-12-01 | 2022-12-31 |  |  | 283 | Yes |  | Yes | 84 | Green
No | No | 114 | 0 | 84 | 367 |  | Implementation | Finance and Accounting | Kathy | Accounts recivable | 2021-12-01 | 2022-12-31 |  |  | 283 | No |  | Yes | 84 | Green
No | No | 115 | 0 | 84 | 367 |  | Implementation | Finance and Accounting | Kathy | Accounts Payable | 2021-12-01 | 2022-12-31 |  |  | 283 | No |  | Yes | 84 | Green
No | No | 135 | 0 | 62 | 339 |  | Implementation | Manager | Carolyn | Ticket Sales | 2021-11-01 | 2022-11-22 |  |  | 277 | Yes | 78FS-90 edays | Yes | 62 | Green
No | No | 136 | 0 | 40 | 194 |  | Implementation | PR | Carolyn | Promotional events | 2021-09-30 | 2022-05-03 |  |  | 154 | Yes | 78FS-120 edays | Yes | 40 | Amber
No | No | 137 | 0 | 40 | 276 |  | Implementation | PR | Carolyn | Radio advertising buys | 2021-09-30 | 2022-08-25 |  |  | 236 | No | 78FS-120 edays | Yes | 40 | Amber
No | No | 138 | 0 | 40 | 276 |  | Implementation | PR | Carolyn | TV advertising buys | 2021-09-30 | 2022-08-25 |  |  | 236 | No | 78FS-120 edays | Yes | 40 | Amber
No | No | 139 | 0 | 118 | 395 |  | Implementation | PR/Band | Carolyn | Promotional Interviews | 2022-01-18 | 2023-02-08 |  |  | 277 | Yes | 78FS-10 edays | Yes | 118 | Green
No | No | 147 | 0 | 116 | 126 |  | Go Live | Band | Jeff | Vancouver, BC | 2022-01-14 | 2022-01-27 |  |  | 10 | Yes |  | Yes | 116 | Green
No | No | 148 | 0 | 147 | 159 |  | Go Live | Band | Jeff | Ottawa, ON | 2022-02-28 | 2022-03-15 |  |  | 12 | Yes | 78FS+30 edays | Yes | 147 | Green
No | No | 149 | 0 | 181 | 191 |  | Go Live | Band | Jeff | Perth, ON | 2022-04-15 | 2022-04-28 |  |  | 10 | Yes | 79FS+30 edays | Yes | 181 | Green
No | No | 150 | 0 | 212 | 227 |  | Go Live | Band | Jeff | Montreal, QB | 2022-05-30 | 2022-06-17 |  |  | 15 | Yes | 80FS+30 edays | Yes | 212 | Green
No | No | 151 | 0 | 237 | 252 |  | Go Live | Band | Jeff | Quebec, QB | 2022-07-04 | 2022-07-22 |  |  | 15 | Yes | 81FS+15 edays | Yes | 237 | Green
No | No | 161 | 0 | 307 | 337 |  | Planning | Travel | Kathy | Hotels | 2022-10-10 | 2022-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | 307 | Green
No | No | 162 | 0 | 307 | 337 |  | Planning | Travel | Kathy | Transportation | 2022-10-10 | 2022-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | 307 | Green
No | No | 164 | 0 | 307 | 397 |  | Planning | Manager | Kathy | Contracts | 2022-10-10 | 2023-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | 307 | Green
No | No | 165 | 0 | 307 | 397 |  | Planning | Manager | Kathy | Ryders | 2022-10-10 | 2023-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | 307 | Green
No | No | 167 | 0 | 307 | 367 |  | Planning | Manager | Kathy | Vehice Leasing | 2022-10-10 | 2022-12-30 |  |  | 60 | No | 118FS-120 edays | Yes | 307 | Green
No | No | 168 | 0 | 307 | 337 |  | Planning | Manager | Kathy | Licensing and Insurance | 2022-10-10 | 2022-11-18 |  |  | 30 | No | 118FS-120 edays | Yes | 307 | Green
No | No | 170 | 0 | 307 | 337 |  | Planning | Human Resources | Kathy | Hiring | 2022-10-10 | 2022-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | 307 | Green
No | No | 171 | 0 | 307 | 337 |  | Planning | Human Resources | Kathy | Training | 2022-10-10 | 2022-11-18 |  |  | 30 | No | 118FS-120 edays | Yes | 307 | Green
No | No | 173 | 0 | 307 | 397 |  | Planning | Logistics | Kathy | Rentals | 2022-10-10 | 2023-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | 307 | Green
No | No | 174 | 0 | 307 | 397 |  | Planning | Logistics | Kathy | Purchasing | 2022-10-10 | 2023-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | 307 | Green
No | No | 175 | 0 | 307 | 337 |  | Planning | Logistics | Kathy | Shipping - Venue to Venue | 2022-10-10 | 2022-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | 307 | Green
No | No | 177 | 0 | 307 | 397 |  | Planning | Creative | Kathy | Promotional Artwork | 2022-10-10 | 2023-02-10 |  |  | 90 | No | 118FS-120 edays | Yes | 307 | Green
No | No | 178 | 0 | 307 | 337 |  | Planning | Vendor | Kathy | Proof Design | 2022-10-10 | 2022-11-18 |  |  | 30 | No | 118FS-120 edays | Yes | 307 | Green
No | No | 179 | 0 | 307 | 321 |  | Planning | Manager | Kathy | Design Approvals | 2022-10-10 | 2022-10-27 |  |  | 14 | Yes | 118FS-120 edays | Yes | 307 | Green
Yes | No | 181 | 0 | 552 | 834 |  | Implementation | Finance and Accounting | Kathy | Payroll | 2023-09-18 | 2024-10-15 |  |  | 282 | Yes | 121FS+30 edays | Yes | 552 | Green
No | No | 182 | 0 | 345 | 627 |  | Implementation | Finance and Accounting | Kathy | Taxes | 2022-12-01 | 2023-12-31 |  |  | 282 | Yes |  | Yes | 345 | Green
No | No | 183 | 0 | 345 | 627 |  | Implementation | Finance and Accounting | Kathy | Accounts recivable | 2022-12-01 | 2023-12-31 |  |  | 282 | No |  | Yes | 345 | Green
No | No | 184 | 0 | 345 | 627 |  | Implementation | Finance and Accounting | Kathy | Accounts Payable | 2022-12-01 | 2023-12-31 |  |  | 282 | No |  | Yes | 345 | Green
No | No | 154 | 0 | 329 | 606 |  | Implementation | Manager | Carolyn | Ticket Sales | 2022-11-09 | 2023-11-30 |  |  | 277 | Yes | 118FS-90 edays | Yes | 329 | Green
No | No | 155 | 0 | 307 | 461 |  | Implementation | PR | Carolyn | Promotional events | 2022-10-10 | 2023-05-11 |  |  | 154 | Yes | 118FS-120 edays | Yes | 307 | Green
No | No | 156 | 0 | 307 | 543 |  | Implementation | PR | Carolyn | Radio advertising buys | 2022-10-10 | 2023-09-04 |  |  | 236 | No | 118FS-120 edays | Yes | 307 | Green
No | No | 157 | 0 | 307 | 543 |  | Implementation | PR | Carolyn | TV advertising buys | 2022-10-10 | 2023-09-04 |  |  | 236 | No | 118FS-120 edays | Yes | 307 | Green
No | No | 158 | 0 | 387 | 664 |  | Implementation | PR/Band | Carolyn | Promotional Interviews | 2023-01-30 | 2024-02-20 |  |  | 277 | Yes | 118FS-10 edays | Yes | 387 | Green
No | No | 16 | 0 | 381 | 393 |  | Go Live | Band | Jeff | Copenhagen, Denmark | 2023-01-20 | 2023-02-06 |  |  | 12 | Yes |  | Yes | 381 | Green
No | No | 28 | 0 | 415 | 433 |  | Go Live | Band | Jeff | Stockholm, Sweden | 2023-03-09 | 2023-04-03 |  |  | 18 | Yes | 118FS+30 edays | Yes | 415 | Green
No | No | 29 | 0 | 415 | 435 |  | Go Live | Band | Jeff | Berlin, Germany | 2023-03-09 | 2023-04-05 |  |  | 20 | Yes | 118FS+30 edays | Yes | 415 | Green
No | No | 30 | 0 | 415 | 425 |  | Go Live | Band | Jeff | Manchester, England | 2023-03-09 | 2023-03-22 |  |  | 10 | Yes | 118FS+30 edays | Yes | 415 | Green

## Raw Schedule
Last Update 10-08-2021 |  | Return to the table of contents
Task Mode | Critical | Summary | Unique ID | % Complete | Days Until Start + | Days Until Finish + | Days Since Completed + | Hub + | Work Stream + | PM + | Task Name | Start | Finish | Actual Start + | Actual Finish + | Duration | Key Deliverable + | Predecessors | Active | Summary2 | RAG +
Manually Scheduled | Yes | Yes | 1 | 8% | 0 days | 0 days |  |  | All | Jeff | Main Event Project Schedule | 4416600% | 4558000% |  |  | 1012 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | Yes | 140 | 24% | -178 days | -177 days |  |  | All | Jeff | US Tour | 4416600% | 4456100% |  |  | 285 days? | No |  | Yes | Yes | -178 days
Auto Scheduled | No | Yes | 2 | 41% | 0 days | 0 days |  |  | All | Jeff | US Tour Planning 2021 | 4416600% | 4456100% |  |  | 285 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | Yes | 3 | 100% | -1 day | 0 days |  | Planning | Travel | Kathy | Booking | 4423700% | 4427800% |  |  | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 32 | 100% | -127 days | -97 days | 97 | Planning | Travel | Kathy | Hotels | 4423700% | 4427800% | 4423700% | 4427800% | 30 days | Yes | 37FS-120 days | Yes | No | -127 days
Auto Scheduled | No | No | 31 | 100% | -127 days | -97 days | 97 | Planning | Travel | Kathy | Transportation | 4423700% | 4427800% | 4423700% | 4427800% | 30 days | Yes | 37FS-120 days | Yes | No | -127 days
Auto Scheduled | No | Yes | 4 | 100% | -1 day | 0 days |  | Planning | Manager | Kathy | Venues | 4423500% | 4435700% |  |  | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 36 | 100% | -129 days | -39 days | 39 | Planning | Manager | Kathy | Contracts | 4423500% | 4435700% | 4423500% | 4435700% | 90 days | Yes | 37FS-120 days | Yes | No | -129 days
Auto Scheduled | No | No | 37 | 100% | -129 days | -39 days | 39 | Planning | Manager | Kathy | Ryders | 4423500% | 4435700% | 4423500% | 4435700% | 90 days | Yes | 37FS-120 days | Yes | No | -129 days
Auto Scheduled | No | Yes | 5 | 100% | -1 day | 0 days |  | Planning | Manager | Kathy | Tour Route | 4428000% | 4436200% |  |  | 60 days | No | 37FS-120 days | Yes | Yes | -1 day
Auto Scheduled | No | No | 33 | 100% | -96 days | -36 days | 36 | Planning | Manager | Kathy | Vehice Leasing | 4428000% | 4436200% | 4428000% | 4436200% | 60 days | No | 37FS-120 edays | Yes | No | -96 days
Auto Scheduled | No | No | 35 | 100% | -96 days | -66 days | 66 | Planning | Manager | Kathy | Licensing and Insurance | 4428000% | 4432000% | 4428000% | 4432000% | 30 days | No | 37FS-120 edays | Yes | No | -96 days
Auto Scheduled | No | Yes | 6 | 100% | -1 day | 0 days |  | Planning | Human Resources | Kathy | Crew | 4423500% | 4427400% |  |  | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 39 | 100% | -129 days | -99 days | 99 | Planning | Human Resources | Kathy | Hiring | 4423500% | 4427400% | 4423500% | 4427400% | 30 days | Yes | 37FS-120 days | Yes | No | -129 days
Auto Scheduled | No | No | 38 | 100% | -129 days | -99 days | 99 | Planning | Human Resources | Kathy | Training | 4423500% | 4427400% | 4423500% | 4427400% | 30 days | No | 37FS-120 days | Yes | No | -129 days
Auto Scheduled | No | Yes | 7 | 100% | -1 day | 0 days |  | Planning | Logistics | Kathy | Equipment | 4423500% | 4435700% |  |  | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 41 | 100% | -129 days | -39 days | 39 | Planning | Logistics | Kathy | Rentals | 4423500% | 4435700% | 4423500% | 4435700% | 90 days | Yes | 37FS-120 days | Yes | No | -129 days
Auto Scheduled | No | No | 42 | 100% | -129 days | -39 days | 39 | Planning | Logistics | Kathy | Purchasing | 4423500% | 4435700% | 4423500% | 4435700% | 90 days | Yes | 37FS-120 days | Yes | No | -129 days
Auto Scheduled | No | No | 40 | 100% | -129 days | -99 days | 99 | Planning | Logistics | Kathy | Shipping - Venue to Venue | 4423500% | 4427400% | 4423500% | 4427400% | 30 days | Yes | 37FS-120 days | Yes | No | -129 days
Auto Scheduled | No | Yes | 8 | 100% | -1 day | 0 days |  | Planning | Creative | Kathy | Merchandising | 4423500% | 4437200% |  |  | 101 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 9 | 100% | -129 days | -28 days | 28 | Planning | Creative | Kathy | Promotional Artwork | 4423500% | 4437200% | 4423500% | 4437200% | 101 days | No | 37FS-120 days | Yes | No | -129 days
Auto Scheduled | No | No | 43 | 100% | -129 days | -74 days | 74 | Planning | Vendor | Kathy | Proof Design | 4423500% | 4430900% | 4423500% | 4430900% | 55 days | No | 37FS-120 days | Yes | No | -129 days
Auto Scheduled | No | No | 44 | 100% | -74 days | -48 days | 48 | Planning | Manager | Kathy | Design Approvals | 4431200% | 4434400% | 4431200% | 4434400% | 26 days | Yes | 22 | Yes | No | -74 days
Auto Scheduled | No | Yes | 11 | 0% | -1 day | 0 days |  | Implementation | Finance and Accounting | Kathy | Finance and Accounting | 4416600% | 4456100% |  |  | 285 days? | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 46 | 0% | -178 days | 107 days |  | Implementation | Finance and Accounting | Kathy | Payroll | 4416600% | 4456100% | 4416600% |  | 285 days | Yes |  | Yes | No | -178 days
Auto Scheduled | No | No | 45 | 0% | -178 days | 107 days |  | Implementation | Finance and Accounting | Kathy | Taxes | 4416600% | 4456100% | 4416600% |  | 285 days? | Yes |  | Yes | No | -178 days
Auto Scheduled | No | No | 48 | 0% | -178 days | 107 days |  | Implementation | Finance and Accounting | Kathy | Accounts recivable | 4416600% | 4456100% | 4416600% |  | 285 days? | No |  | Yes | No | -178 days
Auto Scheduled | No | No | 47 | 0% | -178 days | 107 days |  | Implementation | Finance and Accounting | Kathy | Accounts Payable | 4416600% | 4456100% | 4416600% |  | 285 days? | No |  | Yes | No | -178 days
Auto Scheduled | No | Yes | 12 | 0% | 0 days | 0 days |  |  | All | Jeff | US Pre Tour Events 2021 | 4416600% | 4452500% |  |  | 259 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | Yes | No | 49 | 0% | -150 days | 4 days |  | Planning | Band | Carolyn | Rehearsals | 4420400% | 4441800% | 4420400% |  | 154 days? | Yes | 37FS-240 days | Yes | No | -150 days
Auto Scheduled | No | No | 50 | 0% | -69 days | 81 days |  | Implementation | Manager | Carolyn | Ticket Sales | 4431700% | 4452500% | 4431700% |  | 150 days? | Yes |  | Yes | No | -69 days
Auto Scheduled | No | No | 51 | 0% | -178 days | -24 days |  | Implementation | PR | Carolyn | Promotional events | 4416600% | 4437800% | 4416600% |  | 154 days? | Yes |  | Yes | No | -178 days
Auto Scheduled | No | No | 56 | 0% | -155 days | 81 days |  | Implementation | PR | Carolyn | Radio advertising buys | 4419700% | 4452500% | 4419700% |  | 236 days? | No |  | Yes | No | -155 days
Auto Scheduled | No | No | 55 | 0% | -155 days | 81 days |  | Implementation | PR | Carolyn | TV advertising buys | 4419700% | 4452500% | 4419700% |  | 236 days? | No |  | Yes | No | -155 days
Auto Scheduled | No | No | 54 | 0% | -178 days | 81 days |  | Implementation | PR/Band | Carolyn | Promotional Interviews | 4416600% | 4452500% | 4416600% |  | 259 days? | Yes |  | Yes | No | -178 days
Auto Scheduled | No | Yes | 13 | 0% | 0 days | 0 days |  | Go Live | Band | Jeff | US Tour Year 2021 | 4437900% | 4452500% |  |  | 105 days | No |  | Yes | Yes | 0 days
Auto Scheduled | Yes | No | 20 | 0% | -24 days | -9 days |  | Go Live | Band | Jeff | New York, NY | 4437900% | 4439900% | 4437900% |  | 15 days | Yes |  | Yes | No | -24 days
Auto Scheduled | No | No | 19 | 0% | -7 days | 13 days |  | Go Live | Band | Jeff | Philadelphia, PA | 4440400% | 4443100% | 4440400% |  | 20 days | Yes | 37FS+2 days | Yes | No | -7 days
Auto Scheduled | No | No | 18 | 0% | 15 days | 39 days |  | Go Live | Band | Jeff | Washington, DC | 4443400% | 4446700% |  |  | 24 days | Yes | 38FS+2 days | Yes | No | 15 days
Auto Scheduled | No | No | 17 | 0% | 41 days | 51 days |  | Go Live | Band | Jeff | New Orleans, LA | 4447000% | 4448300% |  |  | 10 days | Yes | 39FS+2 days | Yes | No | 41 days
Auto Scheduled | No | No | 22 | 0% | 56 days | 66 days |  | Go Live | Band | Jeff | Austin, TX | 4449100% | 4450400% |  |  | 10 days | Yes | 40FS+5 days | Yes | No | 56 days
Auto Scheduled | No | No | 21 | 0% | 71 days | 81 days |  | Go Live | Band | Jeff | Los Angeles, CA | 4451200% | 4452500% |  |  | 10 days | Yes | 41FS+5 days | Yes | No | 71 days
Auto Scheduled | No | Yes | 141 | 0% | -178 days | -177 days |  |  | All | Jeff | Canadian Tour | 4446900% | 4496500% |  |  | 355 days? | No |  | Yes | Yes | -178 days
Auto Scheduled | No | Yes | 90 | 0% | 0 days | 0 days |  |  | All | Jeff | Canadian Tour Planning 2022 | 4446900% | 4492600% |  |  | 327 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | Yes | 91 | 0% | -1 day | 0 days |  | Planning | Travel | Kathy | Booking | 4446900% | 4451000% |  |  | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 92 | 0% | 40 days | 70 days |  | Planning | Travel | Kathy | Hotels | 4446900% | 4451000% |  |  | 30 days | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 93 | 0% | 40 days | 70 days |  | Planning | Travel | Kathy | Transportation | 4446900% | 4451000% |  |  | 30 days | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | Yes | 94 | 0% | -1 day | 0 days |  | Planning | Manager | Kathy | Venues | 4446900% | 4459400% |  |  | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 95 | 0% | 40 days | 130 days |  | Planning | Manager | Kathy | Contracts | 4446900% | 4459400% |  |  | 90 days | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 96 | 0% | 40 days | 130 days |  | Planning | Manager | Kathy | Ryders | 4446900% | 4459400% |  |  | 90 days | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | Yes | 97 | 0% | -1 day | 0 days |  | Planning | Manager | Kathy | Tour Route | 4446900% | 4455200% |  |  | 60 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 98 | 0% | 40 days | 100 days |  | Planning | Manager | Kathy | Vehice Leasing | 4446900% | 4455200% |  |  | 60 days | No | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 99 | 0% | 40 days | 70 days |  | Planning | Manager | Kathy | Licensing and Insurance | 4446900% | 4451000% |  |  | 30 days | No | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | Yes | 100 | 0% | -1 day | 0 days |  | Planning | Human Resources | Kathy | Crew | 4446900% | 4451000% |  |  | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 101 | 0% | 40 days | 70 days |  | Planning | Human Resources | Kathy | Hiring | 4446900% | 4451000% |  |  | 30 days | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 102 | 0% | 40 days | 70 days |  | Planning | Human Resources | Kathy | Training | 4446900% | 4451000% |  |  | 30 days | No | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | Yes | 103 | 0% | -1 day | 0 days |  | Planning | Logistics | Kathy | Equipment | 4446900% | 4459400% |  |  | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 104 | 0% | 40 days | 130 days |  | Planning | Logistics | Kathy | Rentals | 4446900% | 4459400% |  |  | 90 days | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 105 | 0% | 40 days | 130 days |  | Planning | Logistics | Kathy | Purchasing | 4446900% | 4459400% |  |  | 90 days | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 106 | 0% | 40 days | 70 days |  | Planning | Logistics | Kathy | Shipping - Venue to Venue | 4446900% | 4451000% |  |  | 30 days | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | Yes | 107 | 0% | -1 day | 0 days |  | Planning | Creative | Kathy | Merchandising | 4446900% | 4459400% |  |  | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 108 | 0% | 40 days | 130 days |  | Planning | Creative | Kathy | Promotional Artwork | 4446900% | 4459400% |  |  | 90 days | No | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 109 | 0% | 40 days | 70 days |  | Planning | Vendor | Kathy | Proof Design | 4446900% | 4451000% |  |  | 30 days | No | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 110 | 0% | 40 days | 54 days |  | Planning | Manager | Kathy | Design Approvals | 4446900% | 4448800% |  |  | 14 days | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | Yes | 111 | 0% | -1 day | 0 days |  | Implementation | Finance and Accounting | Kathy | Finance and Accounting | 4453100% | 4492600% |  |  | 283 days? | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 112 | 0% | 84 days | 367 days |  | Implementation | Finance and Accounting | Kathy | Payroll | 4453100% | 4492600% |  |  | 283 days? | Yes |  | Yes | No | 84 days
Auto Scheduled | No | No | 113 | 0% | 84 days | 367 days |  | Implementation | Finance and Accounting | Kathy | Taxes | 4453100% | 4492600% |  |  | 283 days? | Yes |  | Yes | No | 84 days
Auto Scheduled | No | No | 114 | 0% | 84 days | 367 days |  | Implementation | Finance and Accounting | Kathy | Accounts recivable | 4453100% | 4492600% |  |  | 283 days? | No |  | Yes | No | 84 days
Auto Scheduled | No | No | 115 | 0% | 84 days | 367 days |  | Implementation | Finance and Accounting | Kathy | Accounts Payable | 4453100% | 4492600% |  |  | 283 days? | No |  | Yes | No | 84 days
Auto Scheduled | No | Yes | 133 | 0% | 0 days | 0 days |  |  | All | Jeff | Canadian Pre Tour Events 2022 | 4446900% | 4496500% |  |  | 355 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | No | 134 | 0% | -114 days | 40 days |  | Planning | Band | Carolyn | Rehearsals | 4425600% | 4446800% |  |  | 154 days? | Yes | 78FS-240 days | No | No | -114 days
Auto Scheduled | No | No | 135 | 0% | 62 days | 339 days |  | Implementation | Manager | Carolyn | Ticket Sales | 4450100% | 4488700% |  |  | 277 days? | Yes | 78FS-90 edays | Yes | No | 62 days
Auto Scheduled | No | No | 136 | 0% | 40 days | 194 days |  | Implementation | PR | Carolyn | Promotional events | 4446900% | 4468400% |  |  | 154 days? | Yes | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 137 | 0% | 40 days | 276 days |  | Implementation | PR | Carolyn | Radio advertising buys | 4446900% | 4479800% |  |  | 236 days? | No | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 138 | 0% | 40 days | 276 days |  | Implementation | PR | Carolyn | TV advertising buys | 4446900% | 4479800% |  |  | 236 days? | No | 78FS-120 edays | Yes | No | 40 days
Auto Scheduled | No | No | 139 | 0% | 118 days | 395 days |  | Implementation | PR/Band | Carolyn | Promotional Interviews | 4457900% | 4496500% |  |  | 277 days? | Yes | 78FS-10 edays | Yes | No | 118 days
Auto Scheduled | No | Yes | 146 | 0% | 0 days | 0 days |  | Go Live | Band | Jeff | Canadian Tour year 2022 | 4457500% | 4476400% |  |  | 136 days | No |  | Yes | Yes | 0 days
Auto Scheduled | No | No | 147 | 0% | 116 days | 126 days |  | Go Live | Band | Jeff | Vancouver, BC | 4457500% | 4458800% |  |  | 10 days | Yes |  | Yes | No | 116 days
Auto Scheduled | No | No | 148 | 0% | 147 days | 159 days |  | Go Live | Band | Jeff | Ottawa, ON | 4462000% | 4463500% |  |  | 12 days | Yes | 78FS+30 edays | Yes | No | 147 days
Auto Scheduled | No | No | 149 | 0% | 181 days | 191 days |  | Go Live | Band | Jeff | Perth, ON | 4466600% | 4467900% |  |  | 10 days | Yes | 79FS+30 edays | Yes | No | 181 days
Auto Scheduled | No | No | 150 | 0% | 212 days | 227 days |  | Go Live | Band | Jeff | Montreal, QB | 4471100% | 4472900% |  |  | 15 days | Yes | 80FS+30 edays | Yes | No | 212 days
Auto Scheduled | No | No | 151 | 0% | 237 days | 252 days |  | Go Live | Band | Jeff | Quebec, QB | 4474600% | 4476400% |  |  | 15 days | Yes | 81FS+15 edays | Yes | No | 237 days
Auto Scheduled | Yes | Yes | 145 | 0% | -178 days | -177 days |  | Go Live | Band | Jeff | European Tour Year 2023 | 4484400% | 4558000% |  |  | 527 days? | Yes |  | Yes | Yes | -178 days
Auto Scheduled | Yes | Yes | 159 | 0% | 0 days | 0 days |  |  | All | Jeff | European Tour Planning 2023 | 4484400% | 4558000% |  |  | 527 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | Yes | 160 | 0% | -1 day | 0 days |  | Planning | Travel | Kathy | Booking | 4484400% | 4488300% |  |  | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 161 | 0% | 307 days | 337 days |  | Planning | Travel | Kathy | Hotels | 4484400% | 4488300% |  |  | 30 days | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 162 | 0% | 307 days | 337 days |  | Planning | Travel | Kathy | Transportation | 4484400% | 4488300% |  |  | 30 days | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | Yes | 163 | 0% | -1 day | 0 days |  | Planning | Manager | Kathy | Venues | 4484400% | 4496700% |  |  | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 164 | 0% | 307 days | 397 days |  | Planning | Manager | Kathy | Contracts | 4484400% | 4496700% |  |  | 90 days | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 165 | 0% | 307 days | 397 days |  | Planning | Manager | Kathy | Ryders | 4484400% | 4496700% |  |  | 90 days | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | Yes | 166 | 0% | -1 day | 0 days |  | Planning | Manager | Kathy | Tour Route | 4484400% | 4492500% |  |  | 60 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 167 | 0% | 307 days | 367 days |  | Planning | Manager | Kathy | Vehice Leasing | 4484400% | 4492500% |  |  | 60 days | No | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 168 | 0% | 307 days | 337 days |  | Planning | Manager | Kathy | Licensing and Insurance | 4484400% | 4488300% |  |  | 30 days | No | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | Yes | 169 | 0% | -1 day | 0 days |  | Planning | Human Resources | Kathy | Crew | 4484400% | 4488300% |  |  | 30 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 170 | 0% | 307 days | 337 days |  | Planning | Human Resources | Kathy | Hiring | 4484400% | 4488300% |  |  | 30 days | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 171 | 0% | 307 days | 337 days |  | Planning | Human Resources | Kathy | Training | 4484400% | 4488300% |  |  | 30 days | No | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | Yes | 172 | 0% | -1 day | 0 days |  | Planning | Logistics | Kathy | Equipment | 4484400% | 4496700% |  |  | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 173 | 0% | 307 days | 397 days |  | Planning | Logistics | Kathy | Rentals | 4484400% | 4496700% |  |  | 90 days | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 174 | 0% | 307 days | 397 days |  | Planning | Logistics | Kathy | Purchasing | 4484400% | 4496700% |  |  | 90 days | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 175 | 0% | 307 days | 337 days |  | Planning | Logistics | Kathy | Shipping - Venue to Venue | 4484400% | 4488300% |  |  | 30 days | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | Yes | 176 | 0% | -1 day | 0 days |  | Planning | Creative | Kathy | Merchandising | 4484400% | 4496700% |  |  | 90 days | No |  | Yes | Yes | -1 day
Auto Scheduled | No | No | 177 | 0% | 307 days | 397 days |  | Planning | Creative | Kathy | Promotional Artwork | 4484400% | 4496700% |  |  | 90 days | No | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 178 | 0% | 307 days | 337 days |  | Planning | Vendor | Kathy | Proof Design | 4484400% | 4488300% |  |  | 30 days | No | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 179 | 0% | 307 days | 321 days |  | Planning | Manager | Kathy | Design Approvals | 4484400% | 4486100% |  |  | 14 days | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | Yes | Yes | 180 | 0% | -1 day | 0 days |  | Implementation | Finance and Accounting | Kathy | Finance and Accounting | 4489600% | 4558000% |  |  | 489 days? | No |  | Yes | Yes | -1 day
Manually Scheduled | Yes | No | 181 | 0% | 552 days | 834 days |  | Implementation | Finance and Accounting | Kathy | Payroll | 4518700% | 4558000% |  |  | 282 days | Yes | 121FS+30 edays | Yes | No | 552 days
Auto Scheduled | No | No | 182 | 0% | 345 days | 627 days |  | Implementation | Finance and Accounting | Kathy | Taxes | 4489600% | 4529100% |  |  | 282 days? | Yes |  | Yes | No | 345 days
Auto Scheduled | No | No | 183 | 0% | 345 days | 627 days |  | Implementation | Finance and Accounting | Kathy | Accounts recivable | 4489600% | 4529100% |  |  | 282 days? | No |  | Yes | No | 345 days
Auto Scheduled | No | No | 184 | 0% | 345 days | 627 days |  | Implementation | Finance and Accounting | Kathy | Accounts Payable | 4489600% | 4529100% |  |  | 282 days? | No |  | Yes | No | 345 days
Auto Scheduled | No | Yes | 152 | 0% | 0 days | 0 days |  |  | All | Jeff | European Pre Tour Events 2023 | 4484400% | 4534200% |  |  | 357 days? | No |  | Yes | Yes | 0 days
Auto Scheduled | No | No | 153 | 0% | -114 days | 40 days |  | Planning | Band | Carolyn | Rehearsals | 4425600% | 4446800% |  |  | 154 days? | Yes | 78FS-240 days | No | No | -114 days
Auto Scheduled | No | No | 154 | 0% | 329 days | 606 days |  | Implementation | Manager | Carolyn | Ticket Sales | 4487400% | 4526000% |  |  | 277 days? | Yes | 118FS-90 edays | Yes | No | 329 days
Auto Scheduled | No | No | 155 | 0% | 307 days | 461 days |  | Implementation | PR | Carolyn | Promotional events | 4484400% | 4505700% |  |  | 154 days? | Yes | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 156 | 0% | 307 days | 543 days |  | Implementation | PR | Carolyn | Radio advertising buys | 4484400% | 4517300% |  |  | 236 days? | No | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 157 | 0% | 307 days | 543 days |  | Implementation | PR | Carolyn | TV advertising buys | 4484400% | 4517300% |  |  | 236 days? | No | 118FS-120 edays | Yes | No | 307 days
Auto Scheduled | No | No | 158 | 0% | 387 days | 664 days |  | Implementation | PR/Band | Carolyn | Promotional Interviews | 4495600% | 4534200% |  |  | 277 days? | Yes | 118FS-10 edays | Yes | No | 387 days
Auto Scheduled | No | Yes | 15 | 0% | 0 days | 0 days |  | Go Live | Band | Jeff | European Tour Year 2023 | 4494600% | 4502100% |  |  | 54 days | No |  | Yes | Yes | 0 days
Auto Scheduled | No | No | 16 | 0% | 381 days | 393 days |  | Go Live | Band | Jeff | Copenhagen, Denmark | 4494600% | 4496300% |  |  | 12 days | Yes |  | Yes | No | 381 days
Auto Scheduled | No | No | 28 | 0% | 415 days | 433 days |  | Go Live | Band | Jeff | Stockholm, Sweden | 4499400% | 4501900% |  |  | 18 days | Yes | 118FS+30 edays | Yes | No | 415 days
Auto Scheduled | No | No | 29 | 0% | 415 days | 435 days |  | Go Live | Band | Jeff | Berlin, Germany | 4499400% | 4502100% |  |  | 20 days | Yes | 118FS+30 edays | Yes | No | 415 days
Auto Scheduled | No | No | 30 | 0% | 415 days | 425 days |  | Go Live | Band | Jeff | Manchester, England | 4499400% | 4500700% |  |  | 10 days | Yes | 118FS+30 edays | Yes | No | 415 days

## File Info
Last Update 10-08-2021 |  | Return to the table of contents
Name | Extension | Date accessed | Date modified | Date created | Folder Path
MPUG Class Excel File.xlsx | .xlsx | 2021-10-08 14:01 | 2021-10-06 11:55 | 2021-10-06 09:49 | C:\Users\jchamberlain\Desktop\Tiger Team Reports\MPUG Demo\
MPUG Class Project File.mpp | .mpp | 2021-10-08 14:28 | 2021-10-08 14:29 | 2021-10-06 09:51 | C:\Users\jchamberlain\Desktop\Tiger Team Reports\MPUG Demo\