## Table Of Contents
Table Of Contents
Table Of Contents
Dashboard
RAG Status
Project Manager Status
Task Counts
Tables
Schedule
Raw Schedule
File Info

## Dashboard
Last Update 02-13-2023 |  | Return to the table of contents
Total Status Light--> | 30.59% | Key Status Light Value--> | 29.31% | Critical Path Status Light--> | 66.67% | Set Value Ranges
[6 empty] | Min | Max
red | #N/A | red | #N/A | red | 1 | 41% | 100%
orange | 1 | orange | #N/A | orange | #N/A | 30% | 40%
green | #N/A | green | 1 | green | #N/A | 0% | 30%
| Status | Percentage
Red | 26 | 30.5882
Amber | 20 | 23.5294
Green | 39 | 45.8824

## RAG Status
Last Update 02-13-2023 | Return to the table of contents
|  | Total Status Light--> | 30.59% | Key Status Light Value--> | 29.31% | Critical Path Status Light--> | 66.67% | Set Value Ranges
[8 empty] | Min | Max
|  |  | #N/A | red | #N/A |  | 1 | 41% | 100%
|  |  | 1 | orange | #N/A |  | #N/A | 30% | 40%
|  |  | #N/A | green | 1 |  | #N/A | 0% | 30%

## Project Manager Status
Last Update 02-13-2023 | Return to the table of contents

## Task Counts
Last Update 02-13-2023 | Return to the table of contents

## Tables
Last Update 02-13-2023 |  | Return to the table of contents
Hub by Status |  |  |  |  | Key Milestone Count |  |  | Key Milestone by PM |  |  |  |  | Row Labels | Count of Hub +
Quanty |  |  |  |  | Key | Quantity |  | Key Deliverable + | (All) |  |  |  | Go Live | 19
Hub | Red | Amber | Green | Total | Yes | 58 | [6 empty] | Implementation | 30
Go Live | 2 | 3 | 10 | 15 | No | 27 |  | Quantity | Column Labels |  |  |  | Planning | 63
Implementation | 9 | 3 | 15 | 27 | Total | 85 |  | PM | Carolyn | Jeff | Kathy | Total | Grand Total | 112
Planning | 15 | 14 | 14 | 43 |  |  |  | Red | 6 | 2 | 18 | 26
Total | 26 | 20 | 39 | 85 | Key Deliverable + | Yes |  | Amber | 3 | 3 | 14 | 20 | Row Labels | Count of Work Stream +
[8 empty] | Green | 7 | 10 | 22 | 39 | Band | 16
[5 empty] | Status | Quantity | Percentage | Total | 16 | 15 | 54 | 85 | Creative | 3
Work Stream by Status |  |  |  |  | Red | 17 | 29.31% | [5 empty] | Finance and Accounting | 12
Quantity |  |  |  |  | Amber | 13 | 22.41% | Key Deliverable + | Yes |  |  |  | Human Resources | 6
Work Stream | Red | Amber | Green | Total | Green | 28 | 48.28% | [5 empty] | Logistics | 9
Band | 3 | 3 | 10 | 16 | Total | 58 | 100% | Count of RAG Staus |  |  |  |  | Manager | 18
Creative | 1 | 1 | 1 | 3 |  |  |  | PM | Red | Amber | Green | Total | PR | 9
Finance and Accounting | 4 |  | 8 | 12 | Key Deliverable + | No |  | Carolyn | 4 | 1 | 5 | 10 | PR/Band | 3
Human Resources | 2 | 2 | 2 | 6 |  |  |  | Jeff | 2 | 3 | 10 | 15 | Travel | 6
Logistics | 3 | 3 | 3 | 9 | Status | Quantity | Percentage | Kathy | 11 | 9 | 13 | 33 | Vendor | 3
Manager | 6 | 5 | 7 | 18 | Red | 9 | 33.33% | Total | 17 | 13 | 28 | 58 | Grand Total | 85
PR | 3 | 3 | 3 | 9 | Amber | 7 | 25.93%
PR/Band | 1 |  | 2 | 3 | Green | 11 | 40.74% | Key Deliverable + | No
Travel | 2 | 2 | 2 | 6 | Total | 27 | 100%
Vendor | 1 | 1 | 1 | 3 |  |  |  | Count of RAG Staus
Total | 26 | 20 | 39 | 85 | Key Deliverable + | (All) |  | PM | Red | Amber | Green | Total
[8 empty] | Carolyn | 2 | 2 | 2 | 6
Critical Path | Yes |  |  |  | Status | Quantity | Percentage | Kathy | 7 | 5 | 9 | 21
[5 empty] | Red | 26 | 30.59% | Total | 9 | 7 | 11 | 27
Row Labels | Count of Critical | Percentage |  |  | Amber | 20 | 23.53%
Red | 2 | 66.67% |  |  | Green | 39 | 45.88%
Green | 1 | 33.33% |  |  | Total | 85 | 100%
Grand Total | 3 | 100%

## Schedule
Last Update 02-13-2023 |  | Return to the table of contents
Task Mode | Critical | Summary | Unique ID | % Complete | Days from Start + | Days from Finish + | Days Since Completed + | Hub + | Work Stream + | PM * | Task Name | Start | Finish | Actual Start + | Actual Finish + | Duration | Key Deliverable + | Predecessors | Active | Status (Start) + | Status (Finish) +
Auto Scheduled | No | No | 32 | 0 | -6 | 24 |  | Planning | Travel | Jeff | Hotels | 2023-02-06 | 2023-03-17 |  |  | 30 | Yes | 37FS-120 days | Yes | R | A
Auto Scheduled | No | No | 31 | 0 | -6 | 24 |  | Planning | Travel | Jeff | Transportation | 2023-02-06 | 2023-03-17 |  |  | 30 | Yes | 37FS-120 days | Yes | R | A
Auto Scheduled | No | No | 36 | 1 | -4 | 86 | 107 | Planning | Manager | Bob | Contracts | 2023-02-08 | 2023-06-13 | 44965 | 45090 | 90 | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 37 | 1 | -4 | 86 | 107 | Planning | Manager | Bob | Ryders | 2023-02-08 | 2023-06-13 | 44965 | 45090 | 90 | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 33 | 1 | 29 | 89 | 104 | Planning | Manager | Bob | Vehice Leasing | 2023-03-27 | 2023-06-16 | 45012 | 45093 | 60 | No | 37FS-120 edays | Yes | C | C
Auto Scheduled | No | No | 35 | 1 | 29 | 59 | 134 | Planning | Manager | Bob | Licensing and Insurance | 2023-03-27 | 2023-05-05 | 45012 | 45051 | 30 | No | 37FS-120 edays | Yes | C | C
Auto Scheduled | No | No | 39 | 1 | -4 | 26 | 167 | Planning | Human Resources | Bob | Hiring | 2023-02-08 | 2023-03-21 | 44965 | 45006 | 30 | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 38 | 1 | -4 | 26 | 167 | Planning | Human Resources | Bob | Training | 2023-02-08 | 2023-03-21 | 44965 | 45006 | 30 | No | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 41 | 1 | -4 | 86 | 107 | Planning | Logistics | Sam | Rentals | 2023-02-08 | 2023-06-13 | 44965 | 45090 | 90 | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 42 | 1 | -4 | 86 | 107 | Planning | Logistics | Sam | Purchasing | 2023-02-08 | 2023-06-13 | 44965 | 45090 | 90 | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 40 | 1 | -4 | 26 | 167 | Planning | Logistics | Sam | Shipping - Venue to Venue | 2023-02-08 | 2023-03-21 | 44965 | 45006 | 30 | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 9 | 1 | -4 | 97 | 96 | Planning | Creative | Sam | Promotional Artwork | 2023-02-08 | 2023-06-28 | 44965 | 45105 | 101 | No | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 43 | 1 | -4 | 51 | 142 | Planning | Vendor | Sam | Proof Design | 2023-02-08 | 2023-04-25 | 44965 | 45041 | 55 | No | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 44 | 1 | 51 | 77 | 116 | Planning | Manager | Sam | Design Approvals | 2023-04-26 | 2023-05-31 | 45042 | 45077 | 26 | Yes | 22 | Yes | C | C
Auto Scheduled | No | No | 46 | 0 | -53 | 232 |  | Implementation | Finance and Accounting | Jeff | Payroll | 2022-12-01 | 2024-01-03 |  |  | 285 | Yes |  | Yes | R | G
Auto Scheduled | No | No | 45 | 0 | -53 | 232 |  | Implementation | Finance and Accounting | Jeff | Taxes | 2022-12-01 | 2024-01-03 |  |  | 285 | Yes |  | Yes | R | G
Auto Scheduled | No | No | 48 | 0 | -53 | 232 |  | Implementation | Finance and Accounting | Jeff | Accounts recivable | 2022-12-01 | 2024-01-03 |  |  | 285 | No |  | Yes | R | G
Auto Scheduled | No | No | 47 | 0 | -53 | 232 |  | Implementation | Finance and Accounting | Jeff | Accounts Payable | 2022-12-01 | 2024-01-03 |  |  | 285 | No |  | Yes | R | G
Auto Scheduled | Yes | No | 49 | 0 | -53 | 101 |  | Planning | Band | Bob | Rehearsals | 2022-12-01 | 2023-07-04 |  |  | 154 | Yes | 37FS-240 days | Yes | R | G
Auto Scheduled | No | No | 50 | 0 | 54 | 204 |  | Implementation | Manager | Bob | Ticket Sales | 2023-05-01 | 2023-11-25 |  |  | 150 | Yes |  | Yes | A | G
Auto Scheduled | No | No | 51 | 0 | -53 | 101 |  | Implementation | PR | Bob | Promotional events | 2022-12-01 | 2023-07-04 |  |  | 154 | Yes |  | Yes | R | G
Auto Scheduled | No | No | 56 | 0 | -32 | 204 |  | Implementation | PR | Bob | Radio advertising buys | 2022-12-30 | 2023-11-26 |  |  | 236 | No |  | Yes | R | G
Auto Scheduled | No | No | 55 | 0 | -32 | 204 |  | Implementation | PR | Bob | TV advertising buys | 2022-12-30 | 2023-11-26 |  |  | 236 | No |  | Yes | R | G
Auto Scheduled | No | No | 54 | 0 | -53 | 206 |  | Implementation | PR/Band | Bob | Promotional Interviews | 2022-12-01 | 2023-11-28 |  |  | 259 | Yes |  | Yes | R | G
Auto Scheduled | Yes | No | 20 | 0 | 99 | 114 |  | Go Live | Band | Bob | New York, NY | 2023-07-03 | 2023-07-21 |  |  | 15 | Yes |  | Yes | G | G
Auto Scheduled | No | No | 19 | 0 | 116 | 136 |  | Go Live | Band | Bob | Philadelphia, PA | 2023-07-26 | 2023-08-22 |  |  | 20 | Yes | 37FS+2 days | Yes | G | G
Auto Scheduled | No | No | 18 | 0 | 138 | 162 |  | Go Live | Band | Bob | Washington, DC | 2023-08-25 | 2023-09-27 |  |  | 24 | Yes | 38FS+2 days | Yes | G | G
Auto Scheduled | No | No | 17 | 0 | 164 | 174 |  | Go Live | Band | Bob | New Orleans, LA | 2023-10-02 | 2023-10-13 |  |  | 10 | Yes | 39FS+2 days | Yes | G | G
Auto Scheduled | No | No | 22 | 0 | 179 | 189 |  | Go Live | Band | Bob | Austin, TX | 2023-10-23 | 2023-11-03 |  |  | 10 | Yes | 40FS+5 days | Yes | G | G
Auto Scheduled | No | No | 21 | 0 | 194 | 204 |  | Go Live | Band | Bob | Los Angeles, CA | 2023-11-13 | 2023-11-24 |  |  | 10 | Yes | 41FS+5 days | Yes | G | G
Auto Scheduled | No | No | 92 | 0 | 163 | 193 |  | Planning | Travel | Jeff | Hotels | 2023-09-29 | 2023-11-09 |  |  | 30 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 93 | 0 | 163 | 193 |  | Planning | Travel | Jeff | Transportation | 2023-09-29 | 2023-11-09 |  |  | 30 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 95 | 0 | 163 | 253 |  | Planning | Manager | Bob | Contracts | 2023-09-29 | 2024-02-01 |  |  | 90 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 96 | 0 | 163 | 253 |  | Planning | Manager | Bob | Ryders | 2023-09-29 | 2024-02-01 |  |  | 90 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 98 | 0 | 163 | 223 |  | Planning | Manager | Bob | Vehice Leasing | 2023-09-29 | 2023-12-21 |  |  | 60 | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 99 | 0 | 163 | 193 |  | Planning | Manager | Bob | Licensing and Insurance | 2023-09-29 | 2023-11-09 |  |  | 30 | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 101 | 0 | 163 | 193 |  | Planning | Human Resources | Bob | Hiring | 2023-09-29 | 2023-11-09 |  |  | 30 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 102 | 0 | 163 | 193 |  | Planning | Human Resources | Bob | Training | 2023-09-29 | 2023-11-09 |  |  | 30 | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 104 | 0 | 163 | 253 |  | Planning | Logistics | Bob | Rentals | 2023-09-29 | 2024-02-01 |  |  | 90 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 105 | 0 | 163 | 253 |  | Planning | Logistics | Bob | Purchasing | 2023-09-29 | 2024-02-01 |  |  | 90 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 106 | 0 | 163 | 193 |  | Planning | Logistics | Bob | Shipping - Venue to Venue | 2023-09-29 | 2023-11-09 |  |  | 30 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 108 | 0 | 163 | 253 |  | Planning | Creative | Jeff | Promotional Artwork | 2023-09-29 | 2024-02-01 |  |  | 90 | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 109 | 0 | 163 | 193 |  | Planning | Vendor | Sam | Proof Design | 2023-09-29 | 2023-11-09 |  |  | 30 | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 110 | 0 | 163 | 177 |  | Planning | Manager | Bob | Design Approvals | 2023-09-29 | 2023-10-18 |  |  | 14 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 112 | 0 | 207 | 490 |  | Implementation | Finance and Accounting | Jeff | Payroll | 2023-11-30 | 2024-12-30 |  |  | 283 | Yes |  | Yes | G | G
Auto Scheduled | No | No | 113 | 0 | 207 | 490 |  | Implementation | Finance and Accounting | Jeff | Taxes | 2023-11-30 | 2024-12-30 |  |  | 283 | Yes |  | Yes | G | G
Auto Scheduled | No | No | 114 | 0 | 207 | 490 |  | Implementation | Finance and Accounting | Jeff | Accounts recivable | 2023-11-30 | 2024-12-30 |  |  | 283 | No |  | Yes | G | G
Auto Scheduled | No | No | 115 | 0 | 207 | 490 |  | Implementation | Finance and Accounting | Jeff | Accounts Payable | 2023-11-30 | 2024-12-30 |  |  | 283 | No |  | Yes | G | G
Auto Scheduled | No | No | 135 | 0 | 184 | 461 |  | Implementation | Manager | Jeff | Ticket Sales | 2023-10-30 | 2024-11-19 |  |  | 277 | Yes | 78FS-90 edays | Yes | G | G
Auto Scheduled | No | No | 136 | 0 | 163 | 317 |  | Implementation | PR | Sam | Promotional events | 2023-09-29 | 2024-05-01 |  |  | 154 | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 137 | 0 | 163 | 399 |  | Implementation | PR | Sam | Radio advertising buys | 2023-09-29 | 2024-08-23 |  |  | 236 | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 138 | 0 | 163 | 399 |  | Implementation | PR | Sam | TV advertising buys | 2023-09-29 | 2024-08-23 |  |  | 236 | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 139 | 0 | 241 | 518 |  | Implementation | PR/Band | Bob | Promotional Interviews | 2024-01-17 | 2025-02-06 |  |  | 277 | Yes | 78FS-10 edays | Yes | G | G
Auto Scheduled | No | No | 147 | 0 | 239 | 249 |  | Go Live | Band | Bob | Vancouver, BC | 2024-01-15 | 2024-01-26 |  |  | 10 | Yes |  | Yes | G | G
Auto Scheduled | No | No | 148 | 0 | 269 | 281 |  | Go Live | Band | Bob | Ottawa, ON | 2024-02-26 | 2024-03-12 |  |  | 12 | Yes | 78FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 149 | 0 | 303 | 313 |  | Go Live | Band | Bob | Perth, ON | 2024-04-12 | 2024-04-25 |  |  | 10 | Yes | 79FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 150 | 0 | 334 | 349 |  | Go Live | Band | Bob | Montreal, QB | 2024-05-27 | 2024-06-14 |  |  | 15 | Yes | 80FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 151 | 0 | 359 | 374 |  | Go Live | Band | Bob | Quebec, QB | 2024-07-01 | 2024-07-19 |  |  | 15 | Yes | 81FS+15 edays | Yes | G | G
Auto Scheduled | No | No | 161 | 0 | 430 | 460 |  | Planning | Travel | Bob | Hotels | 2024-10-08 | 2024-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 162 | 0 | 430 | 460 |  | Planning | Travel | Jeff | Transportation | 2024-10-08 | 2024-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 164 | 0 | 430 | 520 |  | Planning | Manager | Bob | Contracts | 2024-10-08 | 2025-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 165 | 0 | 430 | 520 |  | Planning | Manager | Jeff | Ryders | 2024-10-08 | 2025-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 167 | 0 | 430 | 490 |  | Planning | Manager | Bob | Vehice Leasing | 2024-10-08 | 2024-12-30 |  |  | 60 | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 168 | 0 | 430 | 460 |  | Planning | Manager | Jeff | Licensing and Insurance | 2024-10-08 | 2024-11-18 |  |  | 30 | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 170 | 0 | 430 | 460 |  | Planning | Human Resources | Sam | Hiring | 2024-10-08 | 2024-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 171 | 0 | 430 | 460 |  | Planning | Human Resources | Bob | Training | 2024-10-08 | 2024-11-18 |  |  | 30 | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 173 | 0 | 430 | 520 |  | Planning | Logistics | Sam | Rentals | 2024-10-08 | 2025-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 174 | 0 | 430 | 520 |  | Planning | Logistics | Bob | Purchasing | 2024-10-08 | 2025-02-10 |  |  | 90 | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 175 | 0 | 430 | 460 |  | Planning | Logistics | Jeff | Shipping - Venue to Venue | 2024-10-08 | 2024-11-18 |  |  | 30 | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 177 | 0 | 430 | 520 |  | Planning | Creative | Sam | Promotional Artwork | 2024-10-08 | 2025-02-10 |  |  | 90 | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 178 | 0 | 430 | 460 |  | Planning | Vendor | Jeff | Proof Design | 2024-10-08 | 2024-11-18 |  |  | 30 | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 179 | 0 | 430 | 444 |  | Planning | Manager | Bob | Design Approvals | 2024-10-08 | 2024-10-25 |  |  | 14 | Yes | 118FS-120 edays | Yes | G | G
Manually Scheduled | Yes | No | 181 | 0 | 676 | 958 |  | Implementation | Finance and Accounting | Bob | Payroll | 2025-09-17 | 2026-10-15 |  |  | 282 | Yes | 121FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 182 | 0 | 471 | 753 |  | Implementation | Finance and Accounting | Jeff | Taxes | 2024-12-04 | 2026-01-01 |  |  | 282 | Yes |  | Yes | G | G
Auto Scheduled | No | No | 183 | 0 | 471 | 753 |  | Implementation | Finance and Accounting | Sam | Accounts recivable | 2024-12-04 | 2026-01-01 |  |  | 282 | No |  | Yes | G | G
Auto Scheduled | No | No | 184 | 0 | 471 | 753 |  | Implementation | Finance and Accounting | Bob | Accounts Payable | 2024-12-04 | 2026-01-01 |  |  | 282 | No |  | Yes | G | G
Auto Scheduled | No | No | 154 | 0 | 452 | 729 |  | Implementation | Manager | Jeff | Ticket Sales | 2024-11-07 | 2025-11-28 |  |  | 277 | Yes | 118FS-90 edays | Yes | G | G
Auto Scheduled | No | No | 155 | 0 | 430 | 584 |  | Implementation | PR | Jeff | Promotional events | 2024-10-08 | 2025-05-09 |  |  | 154 | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 156 | 0 | 430 | 666 |  | Implementation | PR | Jeff | Radio advertising buys | 2024-10-08 | 2025-09-02 |  |  | 236 | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 157 | 0 | 430 | 666 |  | Implementation | PR | Jeff | TV advertising buys | 2024-10-08 | 2025-09-02 |  |  | 236 | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 158 | 0 | 509 | 786 |  | Implementation | PR/Band | Jeff | Promotional Interviews | 2025-01-27 | 2026-02-17 |  |  | 277 | Yes | 118FS-10 edays | Yes | G | G
Auto Scheduled | No | No | 16 | 0 | 504 | 516 |  | Go Live | Band | Bob | Copenhagen, Denmark | 2025-01-20 | 2025-02-04 |  |  | 12 | Yes |  | Yes | G | G
Auto Scheduled | No | No | 28 | 0 | 538 | 556 |  | Go Live | Band | Bob | Stockholm, Sweden | 2025-03-07 | 2025-04-01 |  |  | 18 | Yes | 118FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 29 | 0 | 538 | 558 |  | Go Live | Band | Bob | Berlin, Germany | 2025-03-07 | 2025-04-03 |  |  | 20 | Yes | 118FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 30 | 0 | 538 | 548 |  | Go Live | Band | Bob | Manchester, England | 2025-03-07 | 2025-03-20 |  |  | 10 | Yes | 118FS+30 edays | Yes | G | G

## Raw Schedule
Last Update 02-13-2023 |  | Return to the table of contents
Task Mode | Critical | Summary | Unique ID | % Complete | Days from Start + | Days from Finish + | Days Since Completed + | Hub + | Work Stream + | PM * | Task Name | Start | Finish | Actual Start + | Actual Finish + | Duration | Key Deliverable + | Predecessors | Active | Status (Start) + | Status (Finish) +
Manually Scheduled | No | Yes | 1 | 8% | 0 | 0 |  |  | All | Bob,Mill | Main Event Project Schedule | 4489600% | 4489600% |  |  | 0 days? | No |  | Yes
Auto Scheduled | No | Yes | 140 | 23% | 0 | 0 |  |  | All | Sam,Mill | US Tour | 4489600% | 4529400% |  |  | 285 days? | No |  | Yes
Auto Scheduled | No | Yes | 2 | 38% | 0 | 0 |  |  | All | Sam,Welder | US Tour Planning 2021 | 4489600% | 4529400% |  |  | 285 days? | No |  | Yes
Auto Scheduled | No | Yes | 3 | 0% | 0 | 0 |  | Planning | Travel | Jeff,Welder | Booking | 4496300% | 4500200% |  |  | 30 days | No |  | Yes
Auto Scheduled | No | No | 32 | 0% | -6 | 24 |  | Planning | Travel | Jeff | Hotels | 4496300% | 4500200% |  |  | 30 days | Yes | 37FS-120 days | Yes | R | A
Auto Scheduled | No | No | 31 | 0% | -6 | 24 |  | Planning | Travel | Jeff | Transportation | 4496300% | 4500200% |  |  | 30 days | Yes | 37FS-120 days | Yes | R | A
Auto Scheduled | No | Yes | 4 | 100% | 0 | 0 |  | Planning | Manager | Bob | Venues | 4496500% | 4509000% |  |  | 90 days | No |  | Yes
Auto Scheduled | No | No | 36 | 100% | -4 | 86 | 107 | Planning | Manager | Bob | Contracts | 4496500% | 4509000% | 4496500% | 4509000% | 90 days | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 37 | 100% | -4 | 86 | 107 | Planning | Manager | Bob | Ryders | 4496500% | 4509000% | 4496500% | 4509000% | 90 days | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | Yes | Yes | 5 | 99% | 0 | 0 |  | Planning | Manager | Bob | Tour Route | 4501200% | 4509300% |  |  | 60 days | No | 37FS-120 days | Yes
Auto Scheduled | No | No | 33 | 100% | 29 | 89 | 104 | Planning | Manager | Bob | Vehice Leasing | 4501200% | 4509300% | 4501200% | 4509300% | 60 days | No | 37FS-120 edays | Yes | C | C
Auto Scheduled | No | No | 35 | 100% | 29 | 59 | 134 | Planning | Manager | Bob | Licensing and Insurance | 4501200% | 4505100% | 4501200% | 4505100% | 30 days | No | 37FS-120 edays | Yes | C | C
Auto Scheduled | No | Yes | 6 | 100% | 0 | 0 |  | Planning | Human Resources | Bob | Crew | 4496500% | 4500600% |  |  | 30 days | No |  | Yes
Auto Scheduled | No | No | 39 | 100% | -4 | 26 | 167 | Planning | Human Resources | Bob | Hiring | 4496500% | 4500600% | 4496500% | 4500600% | 30 days | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 38 | 100% | -4 | 26 | 167 | Planning | Human Resources | Bob | Training | 4496500% | 4500600% | 4496500% | 4500600% | 30 days | No | 37FS-120 days | Yes | C | C
Auto Scheduled | Yes | Yes | 7 | 99% | 0 | 0 |  | Planning | Logistics | Sam | Equipment | 4496500% | 4509000% |  |  | 90 days | No |  | Yes
Auto Scheduled | No | No | 41 | 100% | -4 | 86 | 107 | Planning | Logistics | Sam | Rentals | 4496500% | 4509000% | 4496500% | 4509000% | 90 days | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 42 | 100% | -4 | 86 | 107 | Planning | Logistics | Sam | Purchasing | 4496500% | 4509000% | 4496500% | 4509000% | 90 days | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 40 | 100% | -4 | 26 | 167 | Planning | Logistics | Sam | Shipping - Venue to Venue | 4496500% | 4500600% | 4496500% | 4500600% | 30 days | Yes | 37FS-120 days | Yes | C | C
Auto Scheduled | Yes | Yes | 8 | 99% | 0 | 0 |  | Planning | Creative | Sam | Merchandising | 4496500% | 4510500% |  |  | 101 days | No |  | Yes
Auto Scheduled | No | No | 9 | 100% | -4 | 97 | 96 | Planning | Creative | Sam | Promotional Artwork | 4496500% | 4510500% | 4496500% | 4510500% | 101 days | No | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 43 | 100% | -4 | 51 | 142 | Planning | Vendor | Sam | Proof Design | 4496500% | 4504100% | 4496500% | 4504100% | 55 days | No | 37FS-120 days | Yes | C | C
Auto Scheduled | No | No | 44 | 100% | 51 | 77 | 116 | Planning | Manager | Sam | Design Approvals | 4504200% | 4507700% | 4504200% | 4507700% | 26 days | Yes | 22 | Yes | C | C
Auto Scheduled | No | Yes | 11 | 0% | 0 | 0 |  | Implementation | Finance and Accounting | Jeff | Finance and Accounting | 4489600% | 4529400% |  |  | 285 days? | No |  | Yes
Auto Scheduled | No | No | 46 | 0% | -53 | 232 |  | Implementation | Finance and Accounting | Jeff | Payroll | 4489600% | 4529400% |  |  | 285 days | Yes |  | Yes | R | G
Auto Scheduled | No | No | 45 | 0% | -53 | 232 |  | Implementation | Finance and Accounting | Jeff | Taxes | 4489600% | 4529400% |  |  | 285 days? | Yes |  | Yes | R | G
Auto Scheduled | No | No | 48 | 0% | -53 | 232 |  | Implementation | Finance and Accounting | Jeff | Accounts recivable | 4489600% | 4529400% |  |  | 285 days? | No |  | Yes | R | G
Auto Scheduled | No | No | 47 | 0% | -53 | 232 |  | Implementation | Finance and Accounting | Jeff | Accounts Payable | 4489600% | 4529400% |  |  | 285 days? | No |  | Yes | R | G
Auto Scheduled | Yes | Yes | 12 | 0% | 0 | 0 |  |  | All | Jeff,Bob,Sam | US Pre Tour Events 2021 | 4489600% | 4525800% |  |  | 259 days? | No |  | Yes
Auto Scheduled | Yes | No | 49 | 0% | -53 | 101 |  | Planning | Band | Bob | Rehearsals | 4489600% | 4511100% |  |  | 154 days? | Yes | 37FS-240 days | Yes | R | G
Auto Scheduled | No | No | 50 | 0% | 54 | 204 |  | Implementation | Manager | Bob | Ticket Sales | 4504700% | 4525500% |  |  | 150 days? | Yes |  | Yes | A | G
Auto Scheduled | No | No | 51 | 0% | -53 | 101 |  | Implementation | PR | Bob | Promotional events | 4489600% | 4511100% |  |  | 154 days? | Yes |  | Yes | R | G
Auto Scheduled | No | No | 56 | 0% | -32 | 204 |  | Implementation | PR | Bob | Radio advertising buys | 4492500% | 4525600% |  |  | 236 days? | No |  | Yes | R | G
Auto Scheduled | No | No | 55 | 0% | -32 | 204 |  | Implementation | PR | Bob | TV advertising buys | 4492500% | 4525600% |  |  | 236 days? | No |  | Yes | R | G
Auto Scheduled | No | No | 54 | 0% | -53 | 206 |  | Implementation | PR/Band | Bob | Promotional Interviews | 4489600% | 4525800% |  |  | 259 days? | Yes |  | Yes | R | G
Auto Scheduled | Yes | Yes | 13 | 0% | 0 | 0 |  | Go Live | Band | Bob | US Tour Year 2021 | 4511000% | 4525400% |  |  | 105 days | No |  | Yes
Auto Scheduled | Yes | No | 20 | 0% | 99 | 114 |  | Go Live | Band | Bob | New York, NY | 4511000% | 4512800% |  |  | 15 days | Yes |  | Yes | G | G
Auto Scheduled | No | No | 19 | 0% | 116 | 136 |  | Go Live | Band | Bob | Philadelphia, PA | 4513300% | 4516000% |  |  | 20 days | Yes | 37FS+2 days | Yes | G | G
Auto Scheduled | No | No | 18 | 0% | 138 | 162 |  | Go Live | Band | Bob | Washington, DC | 4516300% | 4519600% |  |  | 24 days | Yes | 38FS+2 days | Yes | G | G
Auto Scheduled | No | No | 17 | 0% | 164 | 174 |  | Go Live | Band | Bob | New Orleans, LA | 4520100% | 4521200% |  |  | 10 days | Yes | 39FS+2 days | Yes | G | G
Auto Scheduled | No | No | 22 | 0% | 179 | 189 |  | Go Live | Band | Bob | Austin, TX | 4522200% | 4523300% |  |  | 10 days | Yes | 40FS+5 days | Yes | G | G
Auto Scheduled | No | No | 21 | 0% | 194 | 204 |  | Go Live | Band | Bob | Los Angeles, CA | 4524300% | 4525400% |  |  | 10 days | Yes | 41FS+5 days | Yes | G | G
Auto Scheduled | No | Yes | 141 | 0% | 0 | 0 |  |  | All | Jeff,Bob,Sam | Canadian Tour | 4519800% | 4569400% |  |  | 355 days? | No |  | Yes
Auto Scheduled | No | Yes | 90 | 0% | 0 | 0 |  |  | All | Jeff,Bob,Sam | Canadian Tour Planning 2022 | 4519800% | 4565600% |  |  | 327 days? | No |  | Yes
Auto Scheduled | No | Yes | 91 | 0% | 0 | 0 |  | Planning | Travel | Jeff | Booking | 4519800% | 4523900% |  |  | 30 days | No |  | Yes
Auto Scheduled | No | No | 92 | 0% | 163 | 193 |  | Planning | Travel | Jeff | Hotels | 4519800% | 4523900% |  |  | 30 days | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 93 | 0% | 163 | 193 |  | Planning | Travel | Jeff | Transportation | 4519800% | 4523900% |  |  | 30 days | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 94 | 0% | 0 | 0 |  | Planning | Manager | Bob | Venues | 4519800% | 4532300% |  |  | 90 days | No |  | Yes
Auto Scheduled | No | No | 95 | 0% | 163 | 253 |  | Planning | Manager | Bob | Contracts | 4519800% | 4532300% |  |  | 90 days | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 96 | 0% | 163 | 253 |  | Planning | Manager | Bob | Ryders | 4519800% | 4532300% |  |  | 90 days | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 97 | 0% | 0 | 0 |  | Planning | Manager | Bob | Tour Route | 4519800% | 4528100% |  |  | 60 days | No |  | Yes
Auto Scheduled | No | No | 98 | 0% | 163 | 223 |  | Planning | Manager | Bob | Vehice Leasing | 4519800% | 4528100% |  |  | 60 days | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 99 | 0% | 163 | 193 |  | Planning | Manager | Bob | Licensing and Insurance | 4519800% | 4523900% |  |  | 30 days | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 100 | 0% | 0 | 0 |  | Planning | Human Resources | Bob | Crew | 4519800% | 4523900% |  |  | 30 days | No |  | Yes
Auto Scheduled | No | No | 101 | 0% | 163 | 193 |  | Planning | Human Resources | Bob | Hiring | 4519800% | 4523900% |  |  | 30 days | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 102 | 0% | 163 | 193 |  | Planning | Human Resources | Bob | Training | 4519800% | 4523900% |  |  | 30 days | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 103 | 0% | 0 | 0 |  | Planning | Logistics | Bob | Equipment | 4519800% | 4532300% |  |  | 90 days | No |  | Yes
Auto Scheduled | No | No | 104 | 0% | 163 | 253 |  | Planning | Logistics | Bob | Rentals | 4519800% | 4532300% |  |  | 90 days | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 105 | 0% | 163 | 253 |  | Planning | Logistics | Bob | Purchasing | 4519800% | 4532300% |  |  | 90 days | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 106 | 0% | 163 | 193 |  | Planning | Logistics | Bob | Shipping - Venue to Venue | 4519800% | 4523900% |  |  | 30 days | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 107 | 0% | 0 | 0 |  | Planning | Creative | Jeff | Merchandising | 4519800% | 4532300% |  |  | 90 days | No |  | Yes
Auto Scheduled | No | No | 108 | 0% | 163 | 253 |  | Planning | Creative | Jeff | Promotional Artwork | 4519800% | 4532300% |  |  | 90 days | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 109 | 0% | 163 | 193 |  | Planning | Vendor | Sam | Proof Design | 4519800% | 4523900% |  |  | 30 days | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 110 | 0% | 163 | 177 |  | Planning | Manager | Bob | Design Approvals | 4519800% | 4521700% |  |  | 14 days | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 111 | 0% | 0 | 0 |  | Implementation | Finance and Accounting | Jeff | Finance and Accounting | 4526000% | 4565600% |  |  | 283 days? | No |  | Yes
Auto Scheduled | No | No | 112 | 0% | 207 | 490 |  | Implementation | Finance and Accounting | Jeff | Payroll | 4526000% | 4565600% |  |  | 283 days? | Yes |  | Yes | G | G
Auto Scheduled | No | No | 113 | 0% | 207 | 490 |  | Implementation | Finance and Accounting | Jeff | Taxes | 4526000% | 4565600% |  |  | 283 days? | Yes |  | Yes | G | G
Auto Scheduled | No | No | 114 | 0% | 207 | 490 |  | Implementation | Finance and Accounting | Jeff | Accounts recivable | 4526000% | 4565600% |  |  | 283 days? | No |  | Yes | G | G
Auto Scheduled | No | No | 115 | 0% | 207 | 490 |  | Implementation | Finance and Accounting | Jeff | Accounts Payable | 4526000% | 4565600% |  |  | 283 days? | No |  | Yes | G | G
Auto Scheduled | No | Yes | 133 | 0% | 0 | 0 |  |  | All | Bob,Jeff,Sam | Canadian Pre Tour Events 2022 | 4519800% | 4569400% |  |  | 355 days? | No |  | Yes
Auto Scheduled | No | No | 134 | 0% | 9 | 163 |  | Planning | Band | Bob | Rehearsals | 4498400% | 4519700% |  |  | 154 days? | Yes | 78FS-240 days | No | A | G
Auto Scheduled | No | No | 135 | 0% | 184 | 461 |  | Implementation | Manager | Jeff | Ticket Sales | 4522900% | 4561500% |  |  | 277 days? | Yes | 78FS-90 edays | Yes | G | G
Auto Scheduled | No | No | 136 | 0% | 163 | 317 |  | Implementation | PR | Sam | Promotional events | 4519800% | 4541300% |  |  | 154 days? | Yes | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 137 | 0% | 163 | 399 |  | Implementation | PR | Sam | Radio advertising buys | 4519800% | 4552700% |  |  | 236 days? | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 138 | 0% | 163 | 399 |  | Implementation | PR | Sam | TV advertising buys | 4519800% | 4552700% |  |  | 236 days? | No | 78FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 139 | 0% | 241 | 518 |  | Implementation | PR/Band | Bob | Promotional Interviews | 4530800% | 4569400% |  |  | 277 days? | Yes | 78FS-10 edays | Yes | G | G
Auto Scheduled | No | Yes | 146 | 0% | 0 | 0 |  | Go Live | Band | Bob | Canadian Tour year 2022 | 4530600% | 4549200% |  |  | 135 days | No |  | Yes
Auto Scheduled | No | No | 147 | 0% | 239 | 249 |  | Go Live | Band | Bob | Vancouver, BC | 4530600% | 4531700% |  |  | 10 days | Yes |  | Yes | G | G
Auto Scheduled | No | No | 148 | 0% | 269 | 281 |  | Go Live | Band | Bob | Ottawa, ON | 4534800% | 4536300% |  |  | 12 days | Yes | 78FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 149 | 0% | 303 | 313 |  | Go Live | Band | Bob | Perth, ON | 4539400% | 4540700% |  |  | 10 days | Yes | 79FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 150 | 0% | 334 | 349 |  | Go Live | Band | Bob | Montreal, QB | 4543900% | 4545700% |  |  | 15 days | Yes | 80FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 151 | 0% | 359 | 374 |  | Go Live | Band | Bob | Quebec, QB | 4547400% | 4549200% |  |  | 15 days | Yes | 81FS+15 edays | Yes | G | G
Auto Scheduled | Yes | Yes | 145 | 0% | 0 | 0 |  | Go Live | Band | Bob | European Tour Year 2023 | 4557300% | 4631000% |  |  | 528 days? | Yes |  | Yes
Auto Scheduled | Yes | Yes | 159 | 0% | 0 | 0 |  |  | All | Jeff,Bob,Sam | European Tour Planning 2023 | 4557300% | 4631000% |  |  | 528 days? | No |  | Yes
Auto Scheduled | No | Yes | 160 | 0% | 0 | 0 |  | Planning | Travel | Sam | Booking | 4557300% | 4561400% |  |  | 30 days | No |  | Yes
Auto Scheduled | No | No | 161 | 0% | 430 | 460 |  | Planning | Travel | Bob | Hotels | 4557300% | 4561400% |  |  | 30 days | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 162 | 0% | 430 | 460 |  | Planning | Travel | Jeff | Transportation | 4557300% | 4561400% |  |  | 30 days | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 163 | 0% | 0 | 0 |  | Planning | Manager | Sam | Venues | 4557300% | 4569800% |  |  | 90 days | No |  | Yes
Auto Scheduled | No | No | 164 | 0% | 430 | 520 |  | Planning | Manager | Bob | Contracts | 4557300% | 4569800% |  |  | 90 days | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 165 | 0% | 430 | 520 |  | Planning | Manager | Jeff | Ryders | 4557300% | 4569800% |  |  | 90 days | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 166 | 0% | 0 | 0 |  | Planning | Manager | Sam | Tour Route | 4557300% | 4565600% |  |  | 60 days | No |  | Yes
Auto Scheduled | No | No | 167 | 0% | 430 | 490 |  | Planning | Manager | Bob | Vehice Leasing | 4557300% | 4565600% |  |  | 60 days | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 168 | 0% | 430 | 460 |  | Planning | Manager | Jeff | Licensing and Insurance | 4557300% | 4561400% |  |  | 30 days | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 169 | 0% | 0 | 0 |  | Planning | Human Resources | Jeff | Crew | 4557300% | 4561400% |  |  | 30 days | No |  | Yes
Auto Scheduled | No | No | 170 | 0% | 430 | 460 |  | Planning | Human Resources | Sam | Hiring | 4557300% | 4561400% |  |  | 30 days | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 171 | 0% | 430 | 460 |  | Planning | Human Resources | Bob | Training | 4557300% | 4561400% |  |  | 30 days | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 172 | 0% | 0 | 0 |  | Planning | Logistics | Jeff | Equipment | 4557300% | 4569800% |  |  | 90 days | No |  | Yes
Auto Scheduled | No | No | 173 | 0% | 430 | 520 |  | Planning | Logistics | Sam | Rentals | 4557300% | 4569800% |  |  | 90 days | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 174 | 0% | 430 | 520 |  | Planning | Logistics | Bob | Purchasing | 4557300% | 4569800% |  |  | 90 days | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 175 | 0% | 430 | 460 |  | Planning | Logistics | Jeff | Shipping - Venue to Venue | 4557300% | 4561400% |  |  | 30 days | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | Yes | 176 | 0% | 0 | 0 |  | Planning | Creative | Jeff | Merchandising | 4557300% | 4569800% |  |  | 90 days | No |  | Yes
Auto Scheduled | No | No | 177 | 0% | 430 | 520 |  | Planning | Creative | Sam | Promotional Artwork | 4557300% | 4569800% |  |  | 90 days | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 178 | 0% | 430 | 460 |  | Planning | Vendor | Jeff | Proof Design | 4557300% | 4561400% |  |  | 30 days | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 179 | 0% | 430 | 444 |  | Planning | Manager | Bob | Design Approvals | 4557300% | 4559000% |  |  | 14 days | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | Yes | Yes | 180 | 0% | 0 | 0 |  | Implementation | Finance and Accounting | Sam | Finance and Accounting | 4563000% | 4631000% |  |  | 487 days? | No |  | Yes
Manually Scheduled | Yes | No | 181 | 0% | 676 | 958 |  | Implementation | Finance and Accounting | Bob | Payroll | 4591700% | 4631000% |  |  | 282 days | Yes | 121FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 182 | 0% | 471 | 753 |  | Implementation | Finance and Accounting | Jeff | Taxes | 4563000% | 4602300% |  |  | 282 days? | Yes |  | Yes | G | G
Auto Scheduled | No | No | 183 | 0% | 471 | 753 |  | Implementation | Finance and Accounting | Sam | Accounts recivable | 4563000% | 4602300% |  |  | 282 days? | No |  | Yes | G | G
Auto Scheduled | No | No | 184 | 0% | 471 | 753 |  | Implementation | Finance and Accounting | Bob | Accounts Payable | 4563000% | 4602300% |  |  | 282 days? | No |  | Yes | G | G
Auto Scheduled | No | Yes | 152 | 0% | 0 | 0 |  |  | All | Jeff,Bob,Sam | European Pre Tour Events 2023 | 4557300% | 4607000% |  |  | 356 days? | No |  | Yes
Auto Scheduled | No | No | 153 | 0% | 9 | 163 |  | Planning | Band | Bob | Rehearsals | 4498400% | 4519700% |  |  | 154 days? | Yes | 78FS-240 days | No | A | G
Auto Scheduled | No | No | 154 | 0% | 452 | 729 |  | Implementation | Manager | Jeff | Ticket Sales | 4560300% | 4598900% |  |  | 277 days? | Yes | 118FS-90 edays | Yes | G | G
Auto Scheduled | No | No | 155 | 0% | 430 | 584 |  | Implementation | PR | Jeff | Promotional events | 4557300% | 4578600% |  |  | 154 days? | Yes | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 156 | 0% | 430 | 666 |  | Implementation | PR | Jeff | Radio advertising buys | 4557300% | 4590200% |  |  | 236 days? | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 157 | 0% | 430 | 666 |  | Implementation | PR | Jeff | TV advertising buys | 4557300% | 4590200% |  |  | 236 days? | No | 118FS-120 edays | Yes | G | G
Auto Scheduled | No | No | 158 | 0% | 509 | 786 |  | Implementation | PR/Band | Jeff | Promotional Interviews | 4568400% | 4607000% |  |  | 277 days? | Yes | 118FS-10 edays | Yes | G | G
Auto Scheduled | No | Yes | 15 | 0% | 0 | 0 |  | Go Live | Band | Bob | European Tour Year 2023 | 4567700% | 4575000% |  |  | 54 days | No |  | Yes
Auto Scheduled | No | No | 16 | 0% | 504 | 516 |  | Go Live | Band | Bob | Copenhagen, Denmark | 4567700% | 4569200% |  |  | 12 days | Yes |  | Yes | G | G
Auto Scheduled | No | No | 28 | 0% | 538 | 556 |  | Go Live | Band | Bob | Stockholm, Sweden | 4572300% | 4574800% |  |  | 18 days | Yes | 118FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 29 | 0% | 538 | 558 |  | Go Live | Band | Bob | Berlin, Germany | 4572300% | 4575000% |  |  | 20 days | Yes | 118FS+30 edays | Yes | G | G
Auto Scheduled | No | No | 30 | 0% | 538 | 548 |  | Go Live | Band | Bob | Manchester, England | 4572300% | 4573600% |  |  | 10 days | Yes | 118FS+30 edays | Yes | G | G

## File Info
Last Update 02-13-2023 |  | Return to the table of contents
Name | Extension | Date accessed | Date modified | Date created | Folder Path
MPUG Class Excel File updated 02132023.xlsx | .xlsx | 2023-02-13 17:34 | 2023-02-13 17:33 | 2023-02-13 17:33 | C:\Users\jchamberlain\OneDrive - Edwards Performance Solutions\Stuff I need - Edwards\MPUG Demo\
MPUG Class Project File revised 02132023.mpp | .mpp | 2023-02-13 17:07 | 2023-02-13 17:07 | 2023-02-13 16:23 | C:\Users\jchamberlain\OneDrive - Edwards Performance Solutions\Stuff I need - Edwards\MPUG Demo\